## Sheet1
Task | Start Date | Duration
Project Selection | 2021-05-17 | 7
Feature Planning | 2021-05-24 | 7
Layout Design | 2021-05-31 | 14
General Health Information | 2021-06-14 | 7
Diet Plan | 2021-06-14 | 7
Specialized Health Information | 2021-06-21 | 7
Menstrual Cycle Tracker for Women | 2021-06-21 | 7
Medicine Reminder | 2021-06-21 | 7
Disease Prediction | 2021-06-28 | 42
MRI/X-ray report analysis | 2021-06-28 | 42
Testing and Debugging | 2021-08-16 | 7
Project Deployment | 2021-08-23 | 7
44444