## Sheet1
Task | start week | duration
Project Selection | 1 | 1
Feature Planning | 2 | 1
Layout Design | 3 | 1.5
Authentication | 4.5 | 1
Medicine Reminder | 5.5 | 2
Menstrual Cycle | 5.5 | 2
General Health Information | 7.5 | 1.5
Specialized Health Information | 7.5 | 1.5
Diet Plan | 9 | 1
Disease Prediction | 10 | 2
Report Analysis | 12 | 2
Testing and Debugging | 15 | 1
Project Deployment | 4.5 | 11.5